## Comparison
Project 1 — Build approach comparison
Inverter Simulator + Modbus Data Logger · 19 Oct 2026
Criterion | Build fast, explain after | Step by step (so far)
Speed | Working end-to-end system in ~1–2 sessions | ~4–5 weeks
Motivation | High: you see the whole thing working from day 1 | Slower; the big picture arrives late
Understanding | Risk of "it works, but I don't know why" | Deeper: each concept tested before the next
Interview risk | If the review is rushed, you can't defend the code | Lower
Portfolio | Ready sooner for job applications | Later
Evidence from Step 1: the code worked, but 2 of 4 first checkpoint answers (scaling, exception 02) were wrong, so a shallow review would leave gaps.

## Hybrid plan
Recommended: hybrid approach
Fast build where it's pure Python, hands-on where software must be installed
# | Phase | What happens | Steps covered | Who does it
1 | Fast build | Claude builds PV model, SunSpec map, live inverter server and data logger in one go, tested before delivery | Steps 2–5 | Claude
2 | See it run | You run the whole system: inverter following a sun curve + SCADA logger polling every few seconds | Steps 2–5 | You
3 | Walkthrough | One file per session: explain → small change + prediction → checkpoint questions | Steps 2–5 | Together
4 | Hands-on build | PostgreSQL, alarms and Docker, installed and built on your PC step by step | Steps 6–8 | Together
Rule: nothing goes on the CV until each file's checkpoints are passed.

## Options
Options to choose from
Mark your choice in column D
Option | Description | Recommended | Your choice (Yes/No)
A | Hybrid: Claude builds Steps 2–5 now, then walkthrough; Steps 6–8 step by step | Yes
B | Build everything (incl. database + Docker) as fast as possible, then review | No
C | Keep going step by step | No
Legend: yellow cells are for you to fill in (dropdown Yes/No). Green row = recommended option.